## REQ
Version 1.0
REQD-01 |  | Secure Mode | guarantee to be private
| REQD-01-001 | 암호화
| REQD-01-002 | user initiate a video feed
| REQD-01-003 | user end a video feed
| REQD-01-004 | user save a video feed for offline review
| REQD-01-005 | user tune image analysis
REQD-01-006
REQD-01-007
REQD-02 |  | Performance | system deliver video as close to real time in real time
| REQD-02-001 |  | real time display (within ?sec delay)
REQD-03 |  | Authentication | 2FA : sign on and keep user credential from compromise | must be handled in a reasonable way
REQD-03-001
REQD-04 |  | Communication Privacy
| REQD-04-001 |  | data sent to user is(remains) private while in transit | No intermediary should be able to snoop or spy
REQD-05 |  | Proof of identity(non-repudiation)
| REQD-05-001 |  | Users use the camera that they believe
REQD-06 |  | Multi-User privacy
| REQD-06-001 |  | Support several users(account) | --> | Admin Mode/Users Mode
REQD-06-002
REQD-07 |  | Reliability | video is reliably delivered
| REQD-07-001 |  | secure connection (in networking)
| REQD-07-002 |  | preformant connection (in networking)
| REQD-07-003 |  | The system can recover from networking errors ASAP
Test Run Mode
Friends.mp4 640x480
REQE-01 |  | Real-time Mode | real time Image projecting | Run Mode
REQE-01-001
REQQ-01 |  | Quality Concerns | in developing
| REQQ-01-001 |  | both apps are architected--> how to prof
| REQQ-01-002 |  | both apps are coded to be secure
| REQQ-01-003 |  | both apps are coded to be free of vuln
REQQ-02
| REQQ-2-001 |  | use bug system(fault/error dectection, recovering, reporting)
REQQ-03
| REQQ-03-001 |  | flowing coding standard
| REQQ-03-001 |  | flowing quality standard
REQQ-04
| REQQ-04-001 |  | QM in same team to test

## Action Items
Schedule
[6 empty] | 1 Week |  |  |  |  | 2 Week |  |  |  |  | 3 Week |  |  |  |  | 4 Week |  |  |  |  | 5 Week
[6 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Phases I
1 week | 1 | Context Analysis |  |  |  | 1 Week M: O; 1 Week T: 1; 1 Week W: 1; 1 Week T: 1; 3 Week F: P; 5 Week F: P
| 2 | Risk Management |  |  |  | 1 Week M: R; 1 Week T: 2; 1 Week F: 2; 3 Week F: R; 5 Week F: R
| 3 | Asset Identification |  |  |  | 1 Week M: I; 1 Week T: 3; 1 Week F: 3; 3 Week F: E; 5 Week F: E
| 4 | Threat Modeling |  |  |  | 1 Week M: E; 1 Week F: 4; 2 Week M: 4; 3 Week F: S; 5 Week F: S
| 4-1 |  | DFD Modeling | bar: 1 Week M; 3 Week F; 5 Week F
| 4-2 |  | Attack Tree |  | N/A | bar: 1 Week M; 3 Week F; 5 Week F
| 4-3 |  | PnG(Misuse case) | bar: 1 Week M; 3 Week F; 5 Week F
| 4-4 |  | STRIDE | bar: 1 Week M; 3 Week F; 5 Week F
| 5 | SEC Risk Assessment | bar: 1 Week M; 3 Week F; 5 Week F
OWASP | bar: 1 Week M; 3 Week F; 5 Week F
HEAVEN | bar: 1 Week M; 3 Week F; 5 Week F
| 6 | SEC Requirement |  |  |  | 1 Week F: 5; 2 Week M: 5; 3 Week F: N; 5 Week F: N
SQUARE
| 7 | Mitigation |  |  |  | 1 Week F: 6; 2 Week M: 6
2 week | 8 | Code Impl |  |  |  | 2 Week M: 8; 2 Week T: 8; 2 Week W: 8; 2 Week T: 8; 2 Week F: 8; 3 Week M: 8; 3 Week T: 8; 3 Week W: 8; 3 Week T: 8
| 8-1 |  | Server(Jetson Nano)
Architect Doc
Development
Code Review
| 8-2 |  | Client(PC)
Architect Doc
Development
Code Review
| 9 | Static Analysis |  |  |  | 2 Week M: 9; 2 Week T: 9; 2 Week W: 9; 2 Week T: 9; 2 Week F: 9; 3 Week M: 9; 3 Week T: 9; 3 Week W: 9; 3 Week T: 9
|  |  | Flaw Finder |  | available
RATS
|  |  | SpotBugs |  | java , N/A
SonarQube
Coverity
3 week | 10 | Fuzz Testing |  |  |  | 3 Week M: 10; 3 Week T: 10; 3 Week W: 10; 3 Week T: 10
| 11 | Penetration Test |  |  |  | 3 Week M: 11; 3 Week T: 11; 3 Week W: 11; 3 Week T: 11
| 12 | Documentation( Integrator ) |  |  |  | 3 Week T: 12; 3 Week W: 12; 3 Week T: 12
| 12-1 |  | Doc
| 12-1 |  | Review
| 13 | Presentation |  |  |  | 3 Week F: 13
Phases II
4 week | 14 | Fuzz Testing |  |  |  | 4 Week M: 14; 4 Week T: 14; 4 Week W: 14; 4 Week T: 14; 4 Week F: 14; 5 Week M: 14; 5 Week T: 14; 5 Week W: 14
| 15 | Penetration Test
5 week | 16 | Presentation |  |  |  | 5 Week W: 16; 5 Week T: 16
| 17 | Documentation( Integrator ) |  |  |  | 5 Week F: 17

## members
안정환 | 책임 | 010-7708-7057 | eidola7@gmail.com
김진모 | 책임 | 010-7677-0561 | iyepp77@gmail.com
박병철 | 책임 | 010-7622-3149 | max.byungchul.park@gmail.com | byungchul.park@lge.com
배경남 | 선임 | 010-3177-0333 | net1692@gmail.com
문성주 | 책임 | 010-2680-6853 | prkitten@gmail.com