## Sheet1
| Risk ID | Condition | Consequence | Probability | Impact | Rating
| R-01 | Not familiar with HW system | it takes a long time to understand HW | 10 | 2 | 20
| R-02 | The development environment is isolated from the external Internet | It spends so much time setting the enviornment and on going project | 8 | 2 | 16
| R-03 | Not familiar with Windows API Programming | It takes a long time to develop a client program. | 5 | 5 | 25
| R-04 | Not familiar with using external libraries (openCV, openSSL, etc.) | Program development takes a long time | 4 | 7 | 28
| R-05 | Lack of TrustZone development knowledge | may not be available | 7 | 7 | 49
| R-06 | Lack of AI knowledge (Face detection & recognition understanding) | It is difficult to derive AI-related threats | 8 | 1 | 8
| R-07 | Communication between PC and target is not secure | Communication data can be leaked | 5 | 10 | 50
| R-08 | The saved image file can be exposed easily | Image data can be leaked | 4 | 10 | 40
| R-10 | Project functional requirements are not clear | False threats can be derived | 6 | 9 | 54
business | R-11 | Too many quizzes and not enough time to project | Project completion may be delayed | 8 | 1 | 8
| R-12 | There are not enough people to run the project. | Project completion may be delayed | 10 | 1 | 10
| R-13 | HW system can be broken (ex: damaged camera cable ) | Project cannot proceed | 2 | 10 | 20
| R-14 | HW system can be stolen | Project cannot proceed | 1 | 10 | 10
● ID: A unique identifier for the risk
● Condition: A statement of fact that describes the risk
● Consequence: a statement indicating the damage cause should the risk occur
● Probability: A score from 1 - 10 indicating the likelihood the risk will occur with 10 being
most certain to occur and 1 being least likely to occur.
● Impact: A score indicating the severity of the damage caused by the risk, with 10 being
most severe to occur and 1 being the least severe.
● Rating: a score of the probability times the impact to determine priority.