## Sheet1
ID |  | Condition | Consequence | Probability | Impact | Rating
Risk ID | Security Risk ID
R-01 |  | Quarantine due to corona virus | Project cannot proceed | 3 | 8 | 24
R-02 |  | H/W system can be broken under no spare parts (ex: damaged camera cable) | Project cannot proceed | 2 | 9 | 18
R-03 |  | Lack of experience of window programming and thirdparty modules | Can not meet the S/W quality | 3 | 6 | 18
R-04 | SR-01 | Communication between PC and target is not secure | Communication data can be leaked | 10 | 8 | 80
R-05 | SR-02 | The saved image file can be exposed easily | Image data can be leaked | 10 | 8 | 80
R-06 |  | Modify specification due to unclear requirement | Project can be delayed or cannot meet the requirement | 3 | 6 | 18
R-07 |  | Too many quizzes and not enough time to project | Project completion may be delayed | 8 | 4 | 32
● ID: A unique identifier for the risk
● Condition: A statement of fact that describes the risk
● Consequence: a statement indicating the damage cause should the risk occur
● Probability: A score from 1 - 10 indicating the likelihood the risk will occur with 10 being most certain to occur and 1 being least likely to occur.
● Impact: A score indicating the severity of the damage caused by the risk, with 10 being most severe to occur and 1 being the least severe.
● Rating: a score of the probability times the impact to determine priority.